## Task List
Task List
Task_ID | Task_Name | Phase | Owner | Start_Date | Duration_Days | End_Date | Pct_Complete | Expected_Pct | Status | Health | Predecessor | Budget_USD | Actual_USD
T01 | Stakeholder interviews | Discovery | Priya Nair | 2025-01-06 | 5 | 2025-01-10 | 100 | 100 | Complete | Green |  | 3500 | 3500
T02 | Requirements gathering | Discovery | Priya Nair | 2025-01-13 | 5 | 2025-01-17 | 100 | 100 | Complete | Green | T01 | 3500 | 3150
T03 | Competitive analysis | Discovery | Tomas Virtanen | 2025-01-13 | 4 | 2025-01-16 | 100 | 100 | Complete | Green | T01 | 2000 | 2000
T04 | Information architecture | Design | Marcus Bergstrom | 2025-01-20 | 5 | 2025-01-24 | 100 | 100 | Complete | Green | T02 | 3000 | 3000
This is a free sample. The full product has 8 sheets with 12+ months of data, all formulas, and charts.